## Slide 1: Time management and project planning
Rob Moore
Lead Consultant, Readify
rob.moore@readify.net
@robdmoore

## Slide 2: Why is it important?
Do you ever feel overwhelmed with:
  Uni classes
  Uni assignments and tests
  Work (multiple jobs?)
  Extracurricular activities
  Maintaining relationships (friends, family, lovers)
  Housework
  Leisure, quiet time, exercising, reading, etc.)
Do you have competing deadlines?

## Slide 3: Why is it important?
You need these skills in the workforce
These skills are important to get right
They help ensure you have a work-life balance

## Slide 4: How can I plan a project and manage my time effectively?

## Slide 5: Golden Triangle

## Slide 6: Continuous loop
Understand
Prioritise
Plan
Execute
Evaluate

## Slide 7: Understand
What are the goal(s)?
Identify high level tasks
What are the deadline(s)?
Breakdown tasks to be prioritisable

## Slide 8: Prioritise
Within and across activities in your life
Prioritisation is the key to avoiding context switching overhead
Decide what to prioritise on:
  Deadline?
  Importance?
  Complexity?

## Slide 9: Plan
Estimate tasks:
  May affect the priority – that’s OK
  Ensure clear scope
Schedule and assign tasks; consider:
  Dependencies
  Deadlines and estimates
  Skillsets
  Remember: things change

## Slide 10: Execute
Plan each week
  Consider non-negotiable things
  Consider what tasks are due soon
  Consider how much time is needed for them
Each day review the activities you planned to refresh your memory

## Slide 11: Evaluate
Regularly evaluate your progress
Consider planned vs actual work
  Things never go to plan – expect it
  Consider what new things you have learnt
  Loop back for another planning cycle
Communicate
Be retrospective – continuously improve

## Slide 12: Continuous loop
Understand
Prioritise
Plan
Execute
Evaluate

## Slide 13: Understand: Example
Project: organise a networking event
Goal: Run event with 50 people from 2 universities
High-level tasks:
  Organise a venue, get people to register, organise food and drinks, secure keynote speaker, etc.
Deadlines:
  Event will be at date (X), Venue needs to be booked (X-4 weeks), people can register by (X-3 weeks), etc.
Breakdown: get people to register:
  Create poster (dependency: secure keynote speaker?), Put up posters, advertise on facebook, create registration page, etc.

## Slide 14: Prioritise: Example
High level prioritisation
Secure keynote speaker (X-6)
Create reg. page / create poster (X-5)
Organise venue (X-4)
Put up posters / create fb page (X-3)
Organise catering (X-1)
etc.

## Slide 15: Plan: Example
High-level task: Secure keynote speaker
(X-8) Joe and Sally – 1 hour meeting
  Decide on list of potential keynote speakers
(X-8/7) Sally and John – 2 hours each ad hoc
  Contact the keynote speakers to see if they are available
(X-6) Joe and Sally – 1 hour meeting
  Decide which speaker to run
  Confirm with the speaker
Items to plan later:
  get bio from speaker (X-4)?
  get slides from speaker (X-2)?
  add introduction to slides and confirm with MC (X-1)?
  confirm with speaker (X-1)?
  send thankyou note and bottle of wine (X+1)?

## Slide 16: Thankyou See slides for bonus content
Rob Moore
Lead Consultant, Readify
rob.moore@readify.net
@robdmoore

## Slide 17: Useful techniques (bonus content)

## Slide 18: Sustainable pace
Consistently sacrificing sleep and weekends isn’t sustainable
The quality and efficiency of your work drops and you get less done
Get help if you need an unsustainable pace to get everything done!

## Slide 19: Task visualisation
Visualising your prioritised todo list helps you focus
It makes you more efficient and helps stop context switching
trello.com

## Slide 20: Pomodoro / Timeboxing
Procrastination is damaging to efficiency
Ensure focus by setting aside a specific amount of time
Take a small break after that time and reflect on what you did
pomodorotechnique.com
workawesome.com/productivity/timeboxing